## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Ingabe Mbayire Melyssa | API IMplementation | m.mbayire@alustudent.com
Murenzi Bonheur | Documentation | m.bonheur@alustudent.com
Teta Butera Nelly | Testing | t.nelly@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| REST API Implementation (CRUD Endpoints using http.server) | Teta Butera Nelly | 2026-01-30 | Completed | Yes | Implemented GET, POST, PUT, DELETE endpoints and tested locally.
| Testing & Validation (curl/Postman + Screenshots), Authentication & Security (Basic Auth + Error Handling) | Ingabe Mbayire Melyssa | 2026-01-30 | Completed | Yes | Captured screenshots of authenticated and unauthorized requests. Added Basic Authentication and handled 401 Unauthorized responses.
| PDF Report Compilation (Security Reflection + DSA Results + Documentation Summary) | Murenzi Bonheur | 2026-01-30 | Completed | Yes | Combined all sections into final structured PDF report.
| UPDATE TEAM SHEET | Teta Butera Nelly | 2026-01-30 | Completed | Yes | Participation details updated and verified by all team members.
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
27th January 2026 | 1. Review assignment requirements 2. Understand modified_sms_v2.xml structure 3. Plan API architecture 4. Allocate tasks | David Neza | Teta Nelly Melyssa Mbayire Bonheur MURENZI | The team analyzed the XML dataset structure and identified key fields such as transaction ID, type, amount, sender, receiver, and timestamp. We discussed how to convert XML records into JSON objects and how to structure CRUD endpoints using http.server. Responsibilities were assigned based on strengths in backend, security, and documentation. | Begin XML parsing and API structure implementation. Set up GitHub repository with required folders.
30th January 2026 | 5. Discuss SQL database implementation approach 6. Plan JSON data modeling 7. Plan JSON data modeling 8. Review GitHub Repository status 9. Update Scrum Board and team sheet The repository structure was verified to ensure required folders (api/, dsa/, docs/, screenshots/) were correctly organized. | David Neza | Teta Nelly Melyssa Mbayire Bonheur MURENZI | The CRUD endpoints were reviewed and tested locally. The team implemented Basic Authentication and discussed its limitations, including credential exposure risks. For DSA integration, we compared linear search and dictionary lookup performance. | Complete DSA performance testing and finalize documentation. Capture testing screenshots using curl/Postman.