## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Teta Butera Nelly | Every team member has a dynamic role and their responsibilities are carried out through completing their assigned tasks as distributed on our scrum board | t.nelly@alustudent.com
Ingabe Mbayire Melyssa |  | m.mbayire@alustudent.com
Bonheur MURENZI |  | m.bonheur@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| setup github team repository | Teta Butera Nelly | 15th January 2026 | Completed | Yes
| Set up Scrum Board using Jira | Ingabe Mbayire Melyssa | 15th January 2026 | Completed | Yes
| Drawing a high-level draft system architecture diagram using Miro | Teta Butera Nelly | 15th January 2026 | Completed | Yes
| Research MoMo SMS XML structure |  | 25th January 2026 | In progress | Yes
| Building and securing a REST API | Bonheur MURENZI | 26th January 2026 | Not started | Yes
| Entity relationship diagram | Teta Butera Nelly | 26th January 2026 | Completed | Yes
| SQL Database Implementation | Bonheur MURENZI | 26th January 2026 | Completed | Yes
| JSON Data Modeling | Ingabe Mbayire Melyssa | 26th January 2026 | Completed | Yes
| UPDATE TEAM SHEET | Bonheur MURENZI | 26th January 2026 | Completed | Yes
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
13th January 2026 | 1. Welcome & Introductions 2.Assignment 3.OverviewUnderstanding the Task | David Neza | Teta Nelly Melyssa Mbayire Bonheur MURENZI | In the first meeting, we discuss the assignment requirements, including objectives, deliverables, and deadlines. we share initial ideas, agree on the scope of work, and decide how tasks will be divided based on individual strengths.we also set a timeline, choose communication tools, and confirm next steps and the next meeting date. | 1.assign tasks to each team member 2.agree on internal deadlines
15th January 2026 | 1. Review progress since the last meeting 2. Individual updates on assigned tasks 3. Discussion of challenges or issues 4. Feedback and improvements 5. Confirm next steps and next meeting date | N/A | Teta Nelly Melyssa Mbayire Bonheur MURENZI | we discuss the progress made by each member and check whether tasks are on schedule. Any problems or difficulties faced during the work addressed, and feedback shared to improve the quality of the assignment. we refine ideas or content if needed, update deadlines, and clearly define the next set of tasks before ending the meeting. | After the meeting, each team member should revise or continue their assigned work based on the feedback received. Outstanding tasks should be completed according to the updated timeline and uploaded to the shared workspace.
22th January 2026 | 1. Review progress from the previous meeting 2. Finalize database requirements and assumptions 3. Discuss and plan ERD design 4.Plan ERD documentation |  | Teta Nelly Melyssa Mbayire Bonheur MURENZI | We discuss the current progress and confirm the finalized database requirements. The ERD structure, including entities, relationships, and constraints, will be reviewed and agreed upon. | After the meeting, the ERD diagram will be created and documented. The SQL database will be implemented based on the approved ERD, followed by the creation of JSON data models. All outputs will be uploaded to the GitHub repository.
26th January 2026 | 5. Discuss SQL database implementation approach .6. Plan JSON data modeling 7. Plan JSON data modeling 8. Review GitHub Repository status 9. Update Scrum Board and team sheet, 10. Confirm Task assignments and deadlines |  | Teta Nelly Melyssa Mbayire Bonheur MURENZI | The approach for SQL database implementation and JSON data modeling will be discussed to ensure consistency with the ERD. We also review the status of the GitHub repository, Scrum board, and team sheet to ensure all project management tools are up to date. | Team members will update the Scrum board to reflect task progress and update the team sheet accordingly. Deadlines will be monitored, and the next meeting will be scheduled to review implementation progress.