## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Teta Butera Nelly | Github Repo Structure | t.nelly@alustudent.com
Ingabe Mbayire Melyssa | Scrum Board | m.mbayire@alustudent.com
Bonheur MURENZI | System architecture Diagram | m.bonheur@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| setup github team repository | Teta Butera Nelly | 15th January 2026 | Completed | Yes
| Set up Scrum Board using Jira | Ingabe Mbayire Melyssa | 15th January 2026 | Completed | Yes
| Drawing a high-level draft system architecture diagram using Miro | Murenzi Bonheur | 15th January 2026 | Completed | Yes
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
13th January 2026 | 1. Welcome & Introductions 2.Assignment 3.OverviewUnderstanding the Task | David Neza | Teta Nelly Melyssa Mbayire Bonheur MURENZI | In the first meeting, we discuss the assignment requirements, including objectives, deliverables, and deadlines. we share initial ideas, agree on the scope of work, and decide how tasks will be divided based on individual strengths.we also set a timeline, choose communication tools, and confirm next steps and the next meeting date. | 1.assign tasks to each team member 2.agree on internal deadlines
15th January 2026 | 1. Review progress since the last meeting 2. Individual updates on assigned tasks 3. Discussion of challenges or issues 4. Feedback and improvements 5. Confirm next steps and next meeting date | David Neza | Teta Nelly Melyssa Mbayire Bonheur MURENZI | we discuss the progress made by each member and check whether tasks are on schedule. Any problems or difficulties faced during the work addressed, and feedback shared to improve the quality of the assignment. we refine ideas or content if needed, update deadlines, and clearly define the next set of tasks before ending the meeting. | After the meeting, each team member should revise or continue their assigned work based on the feedback received. Outstanding tasks should be completed according to the updated timeline and uploaded to the shared workspace.